## 2023-indigenous-natio
2023 Indigenous Nationals | Key Tasks Tracker - EXAMPLE ONLY
Event Policy, Procedure and Guidelines
Name | Subitems | Responsibility
P&G review and updates | Review policies and guideline recommendations from previous year, Send sport guidelines to NSO/SSO to review, Communicate policy and guideline updates to members, Record policy and guideline recommendations into Review, Registration policies, Participation Agreement confirmed | UniSport
Subitems | Name | Responsibility
| Review policies and guideline recommendations from previous year | UniSport
| Send sport guidelines to NSO/SSO to review | UniSport
| Communicate policy and guideline updates to members | UniSport
| Record policy and guideline recommendations into Review | UniSport
| Registration policies, Participation Agreement confirmed | UniSport
Disputes and disciplinaries (D&D) | Review UniSport disputes and disciplinaries process, Appoint convener of committees, Establish dispute and disciplinary committee, Include dispute and disciplinary training into staff briefing, Include dispute and disciplinary processes into UTM pre-event meeting | UniSport
Subitems | Name | Responsibility
| Review UniSport disputes and disciplinaries process | UniSport
| Appoint convener of committees | UniSport
| Establish dispute and disciplinary committee | UniSport
| Include dispute and disciplinary training into staff briefing | UniSport
| Include dispute and disciplinary processes into UTM pre-event meeting | UniSport
Forfeits and fines (F&F) | Review forfeit and fines procedures, Develop forfeit and fines register, Communicate forfeit and fines procedure to UTMs/TMs/Team Captains, Collate forfeit and fines income post event and include in the budget | UniSport
Subitems | Name | Responsibility
| Review forfeit and fines procedures | UniSport
| Develop forfeit and fines register | UniSport
| Communicate forfeit and fines procedure to UTMs/TMs/Team Captains | UniSport
| Collate forfeit and fines income post event and include in the budget | UniSport
Uniform requirements | Review uniform requirements for each sport and update if required | UniSport
Subitems | Name | Responsibility
| Review uniform requirements for each sport and update if required | UniSport
Review competition guidelines for each sport |  | UniSport
Establish organising committee Terms of Reference |  | UniSport
Finance, Legal and Insurance
Name | Subitems | Responsibility
Establish host university event budget |  | Host
Establish UniSport event budget |  | UniSport
Finalise all pre-payments and purchases |  | Both
Obtain and maintain host university agreement |  | Both
Provide UniSport public liability CoC |  | UniSport
Obtain public liability CoC from all stakeholders |  | Host
Obtain risk management plans from host university |  | UniSport
Obtain risk management plans from UniSport |  | Host
Obtain EFTPOS machine from Finance Coordinator |  | UniSport
Keep register of all-event time payments for final banking report |  | UniSport
Finalise purchase orders and payments |  | Both
Finalise host university event budget |  | Host
Finalise UniSport event budget and distribute registration income to host university |  | UniSport
Marketing and Communications
Name | Subitems | Responsibility
Determine key media and marketing stakeholders |  | Both
Create media release for announcement of the event |  | Both
Provide access of NITESG logo to host university |  | UniSport
Design event merchandise |  | Both
Design marketing collateral assets | Social media assets, Registration items, General signage and marketing items, Awards, Sports equipment | Both
Subitems | Name | Responsibility
| Social media assets | Both
| Registration items | Both
| General signage and marketing items | Both
| Awards | Both
| Sports equipment | Both
Add all registered participants into MailChimp |  | UniSport
Develop design brief for all marketing assets |  | Both
Upload brand collateral to website and social media |  | Both
Add listing to ATDW |  | UniSport
Liaise with UniSport for all usernames and passwords to relevant sites |  | Host
Develop social media timeline |  | UniSport
Create social media competition (if applicable) |  | Both
Populate handbook with relevant information | Welcome to Country from elder-in-residence, Welcome note from executive, Welcome note from UniSport executive, Indigenous artwork designs | Both
Subitems | Name | Responsibility
| Welcome to Country from elder-in-residence | Host
| Welcome note from executive | Host
| Welcome note from UniSport executive | UniSport
| Indigenous artwork designs | Host
Publish final handbook on website |  | UniSport
Determine opportunities at university for promotion of the event |  | Host
Determine opportunities for livestreaming |  | Both
Arrange photographer and/or videographer for event |  | Host
Write post-event wrap up article for publishing on website |  | UniSport
Pre-event UTM meeting | Communicate structure of seedings, Communicate all points systems, Outline any major changes to any UniSport or sport guidelines, Communicate team duty requirements, Communicate accreditation collection process, Outline key hubs and locations to UTMs, Welcome guests and acknowledgement of country, Provide details for Opening, Closing, Cultural night, Provide details for catering throughout the week, Outline event-time communications processes | Both
Subitems | Name | Responsibility
| Communicate structure of seedings | UniSport
| Communicate all points systems | UniSport
| Outline any major changes to any UniSport or sport guidelines | UniSport
| Communicate team duty requirements | UniSport
| Communicate accreditation collection process | UniSport
| Outline event-time communications processes | UniSport
| Outline key hubs and locations to UTMs | Host
| Welcome guests and acknowledgement of country | Host
| Provide details for Opening, Closing, Cultural night | Host
| Provide details for catering throughout the week | Host
Set up Stack Team App with all relevant contacts |  | UniSport
Establish Organising Committee meeting dates |  | Both
Registrations and Accreditation
Name | Subitems | Responsibility
Confirm price point for participants |  | Both
Confirm key registration dates (team nomination periods, early bird, late) |  | UniSport
List registration prices and dates on website |  | UniSport
TEAM NOMINATIONS OPEN |  | UniSport
Communicate late entry policy to all members |  | UniSport
Receive accreditation design from Marketing |  | UniSport
Review registration system and information required from it |  | Both
REGISTRATIONS OPEN |  | UniSport
Determine number of lanyards and registration cards required |  | UniSport
Send accreditation design to supplier |  | UniSport
Order accreditation cards |  | UniSport
Order accreditation lanyards |  | UniSport
Develop key contacts list for universities |  | UniSport
Monitor entries and note any issues or errors as they occur |  | UniSport
REGISTRATIONS CLOSE |  | UniSport
Accreditation passes printed and collated by university |  | UniSport
Accreditations distributed to UTMs or Team Captains |  | UniSport
Accreditation passes printed for VIPs, staff, volunteers |  | UniSport
Manage entry changes and replacement passes |  | UniSport
Write post-event registration report |  | UniSport
Sport
Name | Subitems | Responsibility
Confirm order of sports for the week |  | Host
Create max schedule to determine maximum team capacity |  | UniSport
Prepare scoresheets for each sport |  | UniSport
Create offline draws |  | UniSport
Transfer offline draws into Fuse |  | UniSport
Create team duty schedules |  | UniSport
Populate scoresheets with team lists |  | UniSport
Basketball | Book venue, Source referees and umpires, Distribute UniSport guidelines to referee coordinator, Identify sporting equipment required for competition & purchase if needed, Create referee/umpire roster, Distribute fixtures to referee coordinator, Organise technical meeting with referee coordinator and all refs | Both
Subitems | Name | Responsibility
| Book venue | Host
| Source referees and umpires | Host
| Identify sporting equipment required for competition & purchase if needed | Both
| Distribute UniSport guidelines to referee coordinator | Host
| Distribute fixtures to referee coordinator | Host
| Create referee/umpire roster | Host
| Organise technical meeting with referee coordinator and all refs | Both
Netball | Book venue, Source umpires, Identify sporting equipment required for competition & purchase if needed, Ensure spare bibs are available, Distribute UniSport guidelines to referee coordinator, Distribute fixtures to referee coordinator, Create umpire roster, Organise technical meeting with referee coordinator and all refs/umps | Both
Subitems | Name | Responsibility
| Book venue | Host
| Source umpires | Host
| Identify sporting equipment required for competition & purchase if needed | Both
| Ensure spare bibs are available | Both
| Distribute UniSport guidelines to referee coordinator | Host
| Distribute fixtures to referee coordinator | Host
| Create umpire roster | Host
| Organise technical meeting with referee coordinator and all refs/umps | Both
Touch Football | Book venue, Source referees, Identify sporting equipment required for competition & purchase if needed, Order equipment required for competition, Ensure line markings are completed appropriately, Distribute UniSport guidelines to referee coordinator, Distribute fixtures to referee coordinator, Create referee roster, Organise technical meeting with referee coordinator and all refs | Both
Subitems | Name | Responsibility
| Book venue | Host
| Source referees | Host
| Identify sporting equipment required for competition & purchase if needed | Both
| Order equipment required for competition | Host
| Ensure line markings are completed appropriately | Host
| Distribute UniSport guidelines to referee coordinator | Host
| Distribute fixtures to referee coordinator | Host
| Create referee roster | Host
| Organise technical meeting with referee coordinator and all refs | Both
Volleyball | Book venue, Source referees, Identify sporting equipment required for competition & purchase if necessary, Ensure nets are set to appropriate height on all courts, Distribute UniSport guidelines to referee coordinator, Distribute fixtures to referee coordinator, Create referee roster, Organise technical meeting with referee coordinator and all refs | Both
Subitems | Name | Responsibility
| Book venue | Host
| Source referees | Host
| Identify sporting equipment required for competition & purchase if necessary | Both
| Ensure nets are set to appropriate height on all courts | Host
| Distribute UniSport guidelines to referee coordinator | Host
| Distribute fixtures to referee coordinator | Host
| Create referee roster | Host
| Organise technical meeting with referee coordinator and all refs | Both
Review overall results spreadsheet to ensure accurate |  | UniSport
Publish provisional competition schedule on website |  | UniSport
Finalise competition schedule and publish on website and in handbook |  | UniSport
Determine of number of medals, trophies and pennants required for event | Source a supplier to provide medals, trophies and pennants, Order all medals, trophies and pennants | UniSport
Subitems | Name | Responsibility
| Source a supplier to provide medals, trophies and pennants | Both
| Order all medals, trophies and pennants | Host
Confirm location of perpetual trophies and ensure they will be brought |  | UniSport
Create daily poll to collate Spirit votes |  | UniSport
Tally up Spirit votes (minus deductions) and finalise rankings |  | UniSport
Publish each sport results on website daily during event time |  | UniSport
Publish final results on website |  | UniSport
Trophy database updated with current winners/holders of trophies |  | UniSport
Determine wet weather procedures and contingencies |  | Both
Operations
Name | Subitems | Responsibility
Source security requirements and book (if required) |  | Host
Create waste management plans and book additional bins (if required) |  | Host
Determine if additional bathroom arrangements are required |  | Host
Determine shade requirements for outdoor activities and sport |  | Host
Determine spectator and team seating requirements |  | Host
Develop daily run sheet for overall event |  | Both
Create medical directory |  | Host
Develop briefings for event time staff | UniSport staff, Host University staff, Officials, Volunteers, Interns, Sports Medicine/First Aid, Competition Management | Host
Subitems | Name | Responsibility
| UniSport staff | Both
| Host University staff | Host
| Competition Management | Host
| Officials | Host
| Volunteers | Host
| Interns | Host
| Sports Medicine/First Aid | Host
Create site maps and signage plans for all venues |  | Host
Source and purchase any additional signage as required |  | Both
Create equipment inventory list |  | Host
Identify appropriate storage facility for event time equipment |  | Both
Identify Nationals HQ location |  | Both
Confirm delivery address and times with venue for equipment courier |  | UniSport
Arrange for collection of all equipment and signage |  | UniSport
Identify accreditation collection and checking location |  | Host
Confirm catering options for participants | Special events, Daily lunches, Lunch distribution schedule, Dietary requirements | Host
Subitems | Name | Responsibility
| Special events | Host
| Daily lunches | Host
| Lunch distribution schedule | Host
| Dietary requirements | Both
Determine sports medicine requirements and book appropriate coverage |  | Host
Ensure there is an adequate ice supply for first aid |  | Host
Determine power and internet access at all sport venues and offices |  | Host
Workforce - Staffing & Volunteers
Name | Subitems | Responsibility
Create event staffing structure (org. chart) |  | Both
Confirm staff event time roles |  | Both
Create PDs for recruitment | Event time staff, Volunteers, Interns | Host
Subitems | Name | Responsibility
| Event time staff | Host
| Volunteers | Both
| Interns | Host
Create event time staff rosters |  | Both
Staff Travel | Book flights, Circulate itineraries, Book car arrangements, Book accommodation | UniSport
Subitems | Name | Responsibility
| Book flights | UniSport
| Book car arrangements | UniSport
| Book accommodation | UniSport
| Circulate itineraries | UniSport
Establish a volunteer management plan and required volunteer numbers | Advertise volunteer opportunities, Obtain volunteer uniforms, Volunteer training, Volunteer rosters, Volunteer sign in/sign out registers, Volunteer catering, Volunteer registration and induction, Volunteer thank you gifts or function | Host
Subitems | Name | Responsibility
| Advertise volunteer opportunities | Both
| Volunteer registration and induction | UniSport
| Obtain volunteer uniforms | Host
| Volunteer training | Both
| Volunteer rosters | Host
| Volunteer sign in/sign out registers | Host
| Volunteer catering | Host
| Volunteer thank you gifts or function | Host
Special Events & Ceremonies
Name | Subitems | Responsibility
Opening Ceremony | Establish opening ceremony program scope, Source performers that meet the scope of opening ceremony, Identify venue suitable for opening ceremony, Identify a backup venue suitable for opening ceremony, Site plan for opening ceremony venue, Announcement of opening ceremony, List opening ceremony venue on event program, website, and social media, Develop run sheet for opening ceremony, Develop event brief | Host
Subitems | Name | Responsibility
| Establish opening ceremony program scope | Host
| Source performers that meet the scope of opening ceremony | Host
| Identify venue suitable for opening ceremony | Host
| Identify a backup venue suitable for opening ceremony | Host
| Site plan for opening ceremony venue | Host
| Announcement of opening ceremony | Both
| List opening ceremony venue on event program, website, and social media | Both
| Develop run sheet for opening ceremony | Host
| Develop event brief | Host
Medal Presentations | Determine the best location for ceremonies (and backup location ad hoc), Draft run sheet for medal presentations, Determine equipment required for ceremonies, Arrange photographer for ceremonies, Source dignatories for medal presentations, Ensure trophy handover forms are completed, Set up equipment and display trophies and medals | Both
Subitems | Name | Responsibility
| Determine the best location for ceremonies (and backup location ad hoc) | Both
| Draft run sheet for medal presentations | Both
| Determine equipment required for ceremonies | Both
| Arrange photographer for ceremonies | Host
| Source dignatories for medal presentations | Host
| Ensure trophy handover forms are completed | UniSport
| Set up equipment and display trophies and medals | Both
UTM Function | Source suitable venue for UTM function, Identify scope of UTM function e.g. casual drinks or sit down dinner, Review capacity of location and implement ticketing arrangements ad hoc, Add UTM function to event program, Announcement of UTM function, Send invitations to VIPs, Send email invitations to all UTMs and TMs attending, Identify speakers, Develop key notes for speakers | UniSport
Subitems | Name | Responsibility
| Source suitable venue for UTM function | UniSport
| Identify scope of UTM function e.g. casual drinks or sit down dinner | UniSport
| Review capacity of location and implement ticketing arrangements ad hoc | UniSport
| Add UTM function to event program | UniSport
| Announcement of UTM function | UniSport
| Send invitations to VIPs | UniSport
| Send email invitations to all UTMs and TMs attending | UniSport
| Identify speakers | UniSport
| Develop key notes for speakers | UniSport
Cultural and Social activities | Establish cultural / social program scope, Source performers that meet he scope of desired social program (if required), Identify venues suitable for cultural / social activities, Identify backup venues suitable for cultural / social activities, Source site plans for cultural / social activities, Announcement of cultural / social activities, List activities on event program, website, and social media, Develop run sheet for cultural / social activities | Host
Subitems | Name | Responsibility
| Establish cultural / social program scope | Host
| Source performers that meet he scope of desired social program (if required) | Host
| Identify venues suitable for cultural / social activities | Host
| Identify backup venues suitable for cultural / social activities | Host
| Source site plans for cultural / social activities | Host
| Announcement of cultural / social activities | Both
| List activities on event program, website, and social media | Both
| Develop run sheet for cultural / social activities | Host
Sponsorships & Partnerships
Name | Subitems | Responsibility
Write funding applications/acquittal reports (if applicable) |  | Both
Source commercial & community partnerships |  | Both
Manage deliverables of sponsorship agreements as required |  | Both
Engage wider university community for event opportunities | Health students for recovery services, Marketing / media students for placement opportunities, University sports clubs for volunteers, Activation opportunities | Host
Subitems | Name | Responsibility
| Health students for recovery services | Host
| Marketing / media students for placement opportunities | Host
| University sports clubs for volunteers | Host
| Activation opportunities | Host
Evaluation & Reporting
Name | Subitems | Responsibility
Post Event Survey | Determine questions to be sought out in post-event survey, Create post-event survey, Send out post-event survey, Collate responses upon close of post-event survey date, Draw prize winner and send out accordingly, Source post-event survey prize/incentive, Add feedback from post-event survey to Nationals Review | UniSport
Subitems | Name | Responsibility
| Determine questions to be sought out in post-event survey | Both
| Create post-event survey | UniSport
| Source post-event survey prize/incentive | Both
| Send out post-event survey | UniSport
| Collate responses upon close of post-event survey date | UniSport
| Draw prize winner and send out accordingly | UniSport
| Add feedback from post-event survey to Nationals Review | UniSport
UniSport Final Reports | Gather recommendations from all stakeholders, Enter recommendation into Nationals Review database, Write post-event report | UniSport
Subitems | Name | Responsibility
| Gather recommendations from all stakeholders | UniSport
| Enter recommendation into Nationals Review database | UniSport
| Write post-event report | UniSport
Provide a copy of post-event report to UniSport |  | Host
Provide a copy of post-event report to host university |  | UniSport
Conduct organising committee debrief |  | Both